## Slide 1: Планирование и организация
Notes: When you have permission and the problem is chosen and formulated, it is time to look for colleagues that are able and willing to help solving the problem. What kind of experts will be needed? Chief engineer, heat specialist, environmental specialist, economist and so on. We hope you will be able to collect 3-5 collegues.
When the working group is gathered for the first time, you will start your work as an internal CP advisor. You will have to explain our methodology and our slogan: ”Pollution Prevention Pays”, and how you together are going to prove this.

## Slide 2: Получите разрешение
Обсудите с руководством
Опишите необходимые ресурсы
Предложите организацию проекта
Поставьте цели и составьте график
Получите разрешение!

## Slide 3: Что такое проект?
Проект:
ограничен по времени и расходам
имеет однократное действие
преследует конкретную цель
связан с определенным риском

## Slide 4: Планируйте свою работу:
Что необходимо сделать?
Кто из коллег может Вам помочь?
Какую помощь Вы от них ожидаете?
Сколько времени потребуется Вам для выполнения работы?
Какие результаты Вы планируете получить?

## Slide 5: Организуйте свою рабочую группу
Организуйте участников проекта
Представьте ЧП проектной группе
Представьте Ваши идеи по проекту
Составьте план работы
Поставьте главные цели работы
Активизируйте линии коммуникации

## Slide 6: Расчет стоимости
Стадия проекта
Стоимость
Разработка и планирование
Руководство проектом
Оборудование и материалы
Стоимость человеко-часа
Непредвиденные расходы
Всего инвестиций (I0):
Пуско-наладочные работы
Notes: These are the major cost categories to be contained in a project budget. All project planning and –reporting should reflect these categories.

## Slide 7
Сеть
Гистограмма
Ранний
старт
Поздний
старт
Поток
S-кривая
Notes: The ”blue” activities follow one after the other witout any spare time. This is the ”critical path” which defines the neede time span of the project. The ”green” activities have extra time available which means that they can start early or late. When all activities are started as early as possible, we find a S-curve for Early start, and when they are started as late as possible, we get the Late start S-curve. The time space between early and late start we call the Float. To be able to finalize the project on time, you should always try to be in the float area.

## Slide 8
Отработанные часы
Планируемые часы
S-кривая
Гистограмма
Работа 1
Работа 2
Работа 3
Работа 4
Работа 5
Работа 6
время
Время
Человеко-часы
Notes: An example showing the use of the diagrams. In the Bar-chart, blue colour indicates the work already performed. By adding this up, we find how much has been done so far. If we use the S-curve to check man hours, we will find the number of planned man hours for the work done.
From the S-curves we see that the project is delayed and that the used man hours are too high. It is necessary to make changes in the performance of the team to be able to fulfill the project on time and within budget.

## Slide 9: Планирование проекта
Общие аспекты процесса разработки проекта
Планирование и эффективный мониторинг
Анализ рисков
Внедрение проектов – управление и оценка качества
Стандартизация и наилучшие доступные технологии
Notes: Project planing is an extensive subject which has only been superficially described above. Namely the ”General aspects of the project develoåpment process”. The planning process in addition will have to incorporate how project monitoring and control will have to be executed.
No project planning is complete without a risk analysis. Understanding what may og wrong is necessary in order to be able to give attention to the right subjects.
For a successful implementation the project manager must have developed an efficient management model, and must also understand how to secure the quality of the work done.
No work stands alone, the project’s relations to standards and industry practices must be understood so that the outcome is generally relevant.